Guide2. APT Project Development

Capstone Course

Team members:

- Esteban Fierro

- Francisca Herrera

Instructor: Jorge Castro

Section: 002D

1. Progress Summary of the APT Project

| APT Project Progress Summary | To date, we have partially advanced in the ComunicaTEA project, successfully completing Sprint 1 and approximately two-thirds of Sprint 2. Regarding documentation, most of the records required by the Scrum agile methodology have been consolidated, including sprint planning, product backlog, and task tracking. This allows clear control over progress and facilitates future development stages. |
| --- | --- |
| Objectives | Develop a functional prototype of the ComunicaTEA application that facilitates communication using communication cards. Validate the usability of the system with real users. |
| Methodology | The project is being developed using the Scrum agile methodology, as it allows organizing work in short cycles with partial and functional deliveries, which is suitable given the limited time of the semester. |
| Evidence of Progress | To demonstrate progress in the development and documentation of ComunicaTEA, the following resources can be reviewed: - Scrum Agile Methodology Documentation: Documentation - Source Code Repository (Git): GitHub Project These evidences reflect progress in both the prototype implementation and the tracking of planning and development practices. |

2. Work Plan Monitoring

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or Unit of Competence | Activities | Resources | Duration | Responsible | Observations | Progress Status | Adjustments |
| IT Project Management | Requirements gathering | PC, internet connection, PECS guides | 1 week | Francisca Herrera, Esteban Fierro | Basis for defining user stories and project functionalities | Completed | None |
| Data Model Construction | Database design | PC, modeling tools | 1 week | Esteban Fierro, Francisca Herrera | Must be scalable and flexible for new categories and cards | Completed | Minor adjustment: structure added for user preferences |
| Software Solution Development | Application development and digital card implementation | PC, frameworks (Ionic/Angular), documentation | 6 weeks | Esteban Fierro, Francisca Herrera | Restriction: cross-platform compatibility | In progress | Prioritize essential features; secondary improvements to be implemented later |
| Certification Testing | Functional and usability tests | Mobile device, user feedback | 1 week | QA / User | Include feedback from real users | In progress | Second round of tests planned for Sprint 3 |
| Basic English Communication | Basic English documentation | PC, text editor | 1 week | Esteban Fierro, Francisca Herrera | Short manual with main functions | In progress | None |
| IT Project Management | Final project presentation | PowerPoint/Canva presentation | 1 week | Esteban Fierro, Francisca Herrera | Include application demo | Not started | Adjust content based on feedback; include prototype video |

3. Adjustments Based on Monitoring

Factors That Have Facilitated or Hindered Project Development: Facilitating Factors: - Supervisor Feedback: Comments received have clarified project direction, resolved documentation questions (including budgets), and maintained consistency and quality in progress. - Use of Artificial Intelligence: AI has been used to improve document writing and support some programming tasks, streamlining processes and increasing accuracy in documentation and coding. Hindering Factors: - Time Limitation: The limited time available has required prioritizing activities and focusing on critical deliverables, affecting the planned development pace. - Search and Completion of Professional Internship: Searching for and completing the internship has reduced the time and focus available for the project, partially delaying some planned tasks.

Adjusted or Eliminated Activities: During the planning and execution of the project, significant adjustments were made to the original idea. Initially, the ComunicaTEA application was intended to teach about Autism Spectrum Disorder (ASD) and its derivatives, incorporating a concept library and encouraging users to express opinions and emotions through non-verbal communication cards. However, due to time constraints and feedback received from our supervisors, the project focus shifted to the digitalization and modernization of the communication cards, prioritizing the expression of opinions and emotions by users. As a result, some planned activities were modified or eliminated, including the creation of the concept library, to focus resources and effort on developing the main interactive card module. These adjustments allow the project to achieve its objectives more realistically while maintaining the core functionality of supporting communication for users with ASD.

Activities Not Started or Delayed: The activities corresponding to Sprint 3, which mainly involve the implementation of AI for card reading, are delayed due to time limitations and other previously mentioned priorities, such as the professional internship. To advance these activities, the plan is to prioritize the essential functionalities of the AI module, leaving secondary improvements or aesthetic adjustments for later stages. This strategy ensures continued project progress without compromising the quality or core functionality of the application..